| Month |  | Key Deadlines | Perkins V Engagement/State Plan | Local Entity Deadlines |
| --- | --- | --- | --- | --- |
| 2019 | January |  | Write Transition plan |  |
|  | February |  | Feb. 15 Transition Plan to Board of Regents |  |
|  | March | March 14, 2019 | Advisory Meeting I |  |
|  | April | April 1, 2019 April 17, 2019 | Advisory Meeting II Public Hearing 6-8pm (statewide) Begin sub-committee meetings Run baseline data for new indicators |  |
|  | May | May 2, 2019 May 20, 2019 May 24, 2019 | Advisory Meeting III Public Hearing 6-8pm (statewide) Submit Transition Plan to US Department of Education |  |
|  | June | June 3, 2019 | Advisory Meeting IV |  |
|  | July |  | Draft state determined levels of performance |  |
|  | August |  | State Plan Writing Gather Public Comment on State determined levels of performance |  |
|  | September |  | State Plan Writing Gather Public Comment on State determined levels of performance |  |
|  | October |  | Meet with Governor Vet plan with advisory committee, Perkins coordinators and Tier 1 reviewers |  |
|  | November |  | Gather public comment on draft plan Update SWIB |  |
|  | December |  | Gather public comment on draft plan |  |
| 2020 | January |  | Incorporate public comments into state plan and finalize |  |
|  | February |  |  |  |
|  | March |  | Board of Regents to vote on plan approval Submit to governor to sign |  |
|  | April |  | Submit final plan to US Department of Education |  |

Montana Perkins V Timeline