|  |  |  |  |  |
| --- | --- | --- | --- | --- |
| **Month** | | **Key Deadlines** | **Perkins V Engagement/State Plan** | **Local Entity Deadlines** |
| 2019 | January |  | Write Transition plan |  |
| February |  | Feb. 15 Transition Plan to Board of Regents |  |
| March | March 14, 2019 | Advisory Meeting I |  |
| April | April 1, 2019  April 17, 2019 | Advisory Meeting II  Public Hearing 6-8pm (statewide)  Begin sub-committee meetings  Run baseline data for new indicators |  |
| May | May 2, 2019  May 20, 2019  May 24, 2019 | Advisory Meeting III  Public Hearing 6-8pm (statewide)  Submit Transition Plan to US Department of Education |  |
| June | June 3, 2019 | Advisory Meeting IV |  |
| July |  | Draft state determined levels of performance |  |
| August |  | State Plan Writing  Gather Public Comment on State determined levels of performance |  |
| September |  | State Plan Writing  Gather Public Comment on State determined levels of performance |  |
| October |  | Meet with Governor  Vet plan with advisory committee, Perkins coordinators and Tier 1 reviewers |  |
| November |  | Gather public comment on draft plan  Update SWIB |  |
| December |  | Gather public comment on draft plan |  |
| 2020 | January |  | Incorporate public comments into state plan and finalize |  |
| February |  |  |  |
| March |  | Board of Regents to vote on plan approval  Submit to governor to sign |  |
| April |  | Submit final plan to US Department of Education |  |

**Montana Perkins V Timeline**